Student Guide — Phase 1: Project Definition

APT Project “MercadoNacional” (MERNAC) — Private Tenders B2B Marketplace

Course PTY4614 · Capstone · Duoc UC, Puente Alto Campus

# PART I

1. Personal Background

Below is a table with the team members' information.

| Student name | Pablo Renato Carrera Cabello Ignacio Antonio Carrera Cabello |
| --- | --- |
| National ID (RUT) | 20.560.792-7 20.224.646-k |
| Degree program | Ingeniería en Informática |
| Campus | Puente Alto |

2. APT Project Description

Project name, graduate-profile competencies and performance areas put into practice.

| Project name | MercadoNacional (MERNAC) |
| --- | --- |
| Performance area(s) | Web programming, IT project management, database modeling and programming, quality assurance. |
| Competencies | Develop a software solution using techniques that systematize development and maintenance. Manage IT projects, offering alternatives for decision-making. Build data models that scale over time. Perform certification testing of products and processes using industry best practices. |

3. APT Project Rationale

Fields describing the project in detail and justifying its relevance and pertinence.

| Relevance of the APT Project | Every project seeks to respond to a situation or problem. In Chile, the State's own procurement has Mercado Público as a centralized tendering platform, but there is no equivalent for private tenders between companies with an active commercial registration. Today that process happens informally: whoever publishes a project only reaches the suppliers they already know, requirements are stated in free text and reviewed by hand, and no structured record or reputation history follows the company from one process to the next. This topic was chosen because it lets us tackle, at once, four concrete problems of the Chilean private market: (1) discovery limited to the publisher's own network of contacts; (2) manual verification of free-text requirements, with no guarantee that the applicant truly meets them; (3) absence of structured traceability of each process's status; and (4) lack of a behavioral history that travels with the company across processes. It is relevant to the Computer Engineering field because it requires building, from scratch, a system with non-trivial business rules (blocking compliance, automatic closing without scheduled processes, reputation that never decides on its own) on top of a layered architecture verifiable through tests. The project targets the Chilean national market, without limiting itself to a specific region or industry, and its main stakeholders are companies with an active commercial registration —either a natural person with a business activity or a legal entity— that today tender or look for suppliers informally. MERNAC's value contribution is offering, with no intermediaries, a channel to publish and apply with confidence: structured compliance in every application and persistent reputation built from mutual evaluation between publisher and awardee. |
| --- | --- |
| APT Project description | MERNAC is a web platform that lets companies with an active commercial registration —validated against Chile's Tax Service (SII)— publish private tenders with mandatory and desirable requirements, apply to third parties' tenders by declaring, requirement by requirement, whether they comply, and build public reputation with every awarded process through mutual evaluation between publisher and awardee. The platform does not take part in the business itself: it does not process payments, does not decide awards, and does not automatically suspend accounts based on reputation; it only provides the structured information companies need to decide with better judgment. The project will integrate with one external service (the SII, resolved in this phase through SiiMockService) to validate commercial identity, and will ship two Angular applications on top of the same Spring Boot API: one for the business side (companies and visitors) and one for platform administration (fifteen maintainers). |
| Pertinence to the graduate profile | The project is directly related to the graduate profile of the Computer Engineering program, in particular to the competencies of developing a software solution using techniques that systematize development and maintenance; managing IT projects by offering alternatives for decision-making; building data models that scale over time; and performing certification testing of products and processes using industry best practices. These competencies are necessary because MERNAC simultaneously requires a sound software architecture, a data model that enforces strict business rules, and a test suite that backs up every rule. |
| Relation to professional interests | Our professional interests are related to hands-on work building complete software systems: software design and architecture, backend and frontend development, database modeling, interface design and quality assurance. These interests are directly reflected in the project, since MERNAC requires covering each of these areas within a team of only two people. Developing this project brings us closer to the reality we will face upon graduating, since it requires making design, planning and quality decisions under the same time and resource constraints as a real software project. |
| Feasibility of developing the APT Project | The Capstone course (PTY4614) runs for 18 weeks (26-08-2026 to 30-12-2026), with a dedication of 20 hours per week per team member (40 person-hours per week for the team, 720 person-hours in total according to the Work Breakdown Structure). The required materials are: (1) computers for development and documentation; (2) Angular and Java 21 with Spring Boot for frontend and backend; (3) PostgreSQL as the database engine; and (4) Docker and Docker Compose for containerized deployment. There are no external factors preventing the project's development: the only real external dependency, the SII service for validating RUT and business activity, is resolved in this phase through SiiMockService, a test double with the same interface the real service would have, isolated behind a service interface so it can be swapped out without impacting the rest of the business layer. The main factor to monitor is that the two-person team covers all five WBS roles (Project Manager, Programmer Analyst, DBA, QA and Designer); this is mitigated with weekly syncs to review progress and risks, and with a backlog of ten milestones worked strictly in order. Given the planned scope (42 functional requirements, 23 non-functional requirements and 24 use cases) and the committed weekly dedication, developing the project is feasible within the 18 weeks of the academic term. |

# PART II

4. Objectives

General and specific objectives of the APT Project.

| General objective | Develop a B2B marketplace web platform (MercadoNacional / MERNAC) that lets companies with a commercial registration publish and apply to private tenders, validating requirement compliance and building reputation for every awarded process. |
| --- | --- |
| Specific objectives | Implement registration and authentication with RUT and business-activity validation against the SII. Develop tender publishing with mandatory/desirable requirements and bidding documents. Implement applications with a blocking compliance declaration for mandatory requirements. Build the comparison matrix and the award process with a stated reason. Implement mutual evaluation, reputation calculation and prestige levels. Deliver traceability panels, an audit log and two reports exportable to PDF/XLS. Integrate email notifications for the system's eight action events. Build the secondary maintainers application (15 administrative maintainers). |

5. Methodology

Working methodology used to carry out the APT Project.

Methodology description The waterfall methodology will be used, with five sequential phases: Planning, Analysis and Design, Development, Testing and QA, and Implementation and Closure. This classic methodology was chosen —rather than a purely agile approach— because the system's requirements (42 FR, 23 NFR and 21 business rules) can be precisely specified from the start through the ERS Report and the Use-Case Document, and because the academic team is assessed phase by phase, with well-defined deliverables and milestones (Project Charter in week 2, Analysis and Design closing in week 6, project closure in week 18). Within the Development phase, work is organized into ten sequential milestones (H0 to H9) defined in the construction backlog: each milestone corresponds to one or more work packages of the Work Breakdown Structure and is fully closed —including its tests— before moving to the next one, without getting ahead on later modules even if they look simple. This way of working combines the traceability typical of the classic methodology with an incremental execution order within each phase. Since the project is a group effort, tasks are distributed according to the five roles of the Work Breakdown Structure: Pablo Renato Carrera Cabello takes on the roles of Project Manager and Programmer Analyst (project coordination, architecture, backend and frontend development, SII integration); Ignacio Antonio Carrera Cabello takes on the roles of DBA, QA and Designer (data model and PostgreSQL, mockups and interface, unit and integration testing). Both take part in scope and planning decisions and sync weekly to review progress and risks.

6. Evidence

Evidence to be assessed in the progress report and in the final report of the APT Project.

| Evidence type(progress or final) | Evidence name | Description | Justification |
| --- | --- | --- | --- |
| Progress | APT Project Definition | Document defining the APT Project to be carried out (this guide). | Define the project to be developed throughout the Capstone. |
| Progress | Project Charter | Initial document of the project phase defining the project's boundaries. | Understand the project's boundaries, objectives, risks and budget. |
| Progress | ERS Report | Software requirements specification under IEEE 830. | Present the proposal and requirement specifications of the project. |
| Progress | Requirements Sheet | Document with the system's 42 functional and 23 non-functional requirements. | Understand the system's requirements to build the solution. |
| Progress | Extended Use-Case Document | Document describing the 24 user interactions with the system (CU-01 to CU-24). | Present the user's interactions with the system. |
| Progress | Mockups and navigable prototype | Mockup and semi-functional HTML prototype with every view of the project. | Visually present how the system looks. |
| Progress | WBS Matrix and Phase Costs | Task breakdown with hours per role and costing per phase. | Plan and cost the project's effort in person-hours. |
| Progress | Gantt Chart | Project schedule distributed across the term's 18 weeks. | Organize the dates for carrying out the project's activities. |
| Progress | Architecture Document (DAS) | Document defining the software architecture and the system's quality requirements. | Define the system's quality requirements and technical design. |
| Final | Main and secondary web applications | Delivery of 100% of the system (Angular + Spring Boot + PostgreSQL) with all modules and the maintainers panel. | Delivery of the complete product committed to in the Charter. |
| Final | Automated test suite | Unit and integration tests covering the 21 business rules. | Certify the quality of the product and its processes. |
| Final | User manuals and training | Document describing the system's use for end users. | Give the user a guide for operating the system. |
| Final | Project closure act | Document formalizing the project's closure. | Mark the product's development process as finished. |

7. Work Plan

APT Project planning by competency, activity, resources, duration and person responsible.

| Competency or competency unit | Activity/Task name | Description | Resources | Activity duration | Responsible | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| Project management | Project Charter | Define scope, objectives, team, milestones, budget and initial risks of the project. | Computer and Project Charter template | Wk. 1 (26-08 a 01-09) | Pablo Carrera (PM/Analyst) | Uses charters from previous projects as a formatting reference. |
| Project management | Team organization | Distribute the five WBS roles (Project Manager, Programmer Analyst, DBA, QA, Designer) between the two team members. | Computer and WBS Matrix | Wk. 1 (26-08 a 01-09) | Whole team | A 2-person team covering 5 roles is logged as a risk in the Charter. |
| Project management | Charter approval | Validate the Project Charter with the guiding instructor and formally close the Planning phase. | Computer and Charter document | Wk. 2 (02-09 a 08-09) | Pablo Carrera (PM/Analyst) | Charter milestone: Planning closes in week 2. |
| Requirements analysis | General requirements definition | Identify the system's modules and needs at a high level (Accounts, Tenders, Applications, Award, Reputation, Reports, Administration). | Computer and documents | Wk. 2 (02-09 a 08-09) | Whole team | Basis for the next phase's Requirements Sheet. |
| Requirements analysis | Specific requirements capture | Detail the system's 42 functional and 23 non-functional requirements. | Computer and Requirements Sheet | Wk. 3 (09-09 a 15-09) | Whole team | Uses the project's already-drafted functional specification. |
| Software architecture | Software architecture document (DAS) | Define the layered architecture, the technology stack and the system's quality requirements. | Computer and documents | Wk. 4 (16-09 a 22-09) | Pablo Carrera (PM/Analyst) | Builds on work from the Architecture course. |
| Software analysis and design | Extended use-case document | Draft the system's 24 use cases (CU-01 to CU-24), with their normal and alternative flows. | Computer and documents | Wk. 4 (16-09 a 22-09) | Whole team | A use case without its alternative flows is considered incomplete. |
| Interface design | Mockups and navigable prototype | Build the mockups and the navigable HTML prototype of the four business applications and the fifteen maintainers. | Computer and internet (mockup tool) | Wk. 5 (23-09 a 29-09) | Ignacio Carrera (DBA/QA/Designer) | Helps determine the system's final design before coding starts. |
| Project documentation | ERS report and requirements sheet | Draft the ERS Report under IEEE 830 and close the Analysis and Design phase. | Computer and documents | Wk. 6 (30-09 a 06-10) | Whole team | Charter milestone: Analysis and Design closes in week 6. |
| Software development | H0 · Project scaffolding | Set up backend, frontend and Docker containers with no business logic, until the full stack responds. | Computer, Docker, Spring Boot, Angular | Wk. 7 (07-10 a 13-10) | Pablo Carrera (PM/Analyst) | Closes when /api/salud responds and both SPAs load. |
| Database modeling and programming | H1 · Data and catalogs (DB scripts and PL/SQL queries) | Create the full schema, seed catalogs and required queries in PostgreSQL. | Computer and PostgreSQL | Wk. 8 (14-10 a 20-10) | Ignacio Carrera (DBA/QA/Designer) | Needed so the rest of the modules can be built on real data. |
| Software development / cybersecurity | H2 · Security, accounts and SII validation | Implement registration with RUT validation against SiiMockService, authentication, roles and sessions. | Computer, Spring Security, JWT | Wk. 9 (21-10 a 27-10) | Pablo Carrera (PM/Analyst) | Foundation of the whole system's authentication; cannot be left for the end. |
| Software development | H3 · Tenders and lazy closing | Implement publishing, editing, cancellation and automatic closing (without scheduled processes) of tenders. | Computer, Angular, Spring Boot | Wk. 10 (28-10 a 03-11) | Pablo Carrera (PM/Analyst) | Lazy closing is resolved only when the tender is accessed. |
| Software development | H4 · Applications and blocking compliance | Implement the requirement-by-requirement compliance declaration, blocking submission if a mandatory one is missing. | Computer, Angular, Spring Boot | Wk. 11 (04-11 a 10-11) | Pablo Carrera (PM/Analyst) | This is the heart of the product: without it, MERNAC is just a bulletin board. |
| Software development | H5 · Award and comparison matrix | Implement applicant comparison, award with a stated reason, and declaring a tender void. | Computer, Angular, Spring Boot | Wk. 12 (11-11 a 17-11) | Pablo Carrera (PM/Analyst) | Reputation never sorts by default nor discards applicants. |
| Software development | H6 · Reputation and prestige levels | Implement mutual evaluation, reputation calculation and prestige levels. | Computer, Angular, Spring Boot | Wk. 13 (18-11 a 24-11) | Whole team | Closes the cycle: past behavior travels with the company. |
| Software development | H7 · Traceability and reports (RPT-01/RPT-02) | Implement the audit log and the two reports exportable to PDF and XLS. | Computer, PDF/XLS export libraries | Wk. 14 (25-11 a 01-12) | Pablo Carrera (PM/Analyst) | Reports respect the same filters as the on-screen view. |
| Software development | H8 · Secondary application (15 maintainers) | Build the administration application with the fifteen maintainers and evaluation moderation. | Computer, Angular | Wk. 14 (25-11 a 01-12) | Ignacio Carrera (DBA/QA/Designer) | All fifteen maintainers follow the same screen pattern. |
| Quality assurance | Test environment setup | Prepare the environment and data needed to run the test suite. | Computer, JUnit, Mockito, Karma | Wk. 15 (02-12 a 08-12) | Ignacio Carrera (DBA/QA/Designer) | Basis for functional tests to run in a controlled environment. |
| Quality assurance | Functional testing | Verify that all 21 business rules (RN-01 to RN-21) have at least one test case. | Computer, JUnit, Mockito, Spring Boot Test | Wk. 15 (02-12 a 08-12) | Ignacio Carrera (DBA/QA/Designer) | Tests the product's quality level before moving to user testing. |
| Quality assurance | User testing | Validate the full publish → apply → award → evaluate flow with test data. | Computer and demo script | Wk. 16 (09-12 a 15-12) | Ignacio Carrera (DBA/QA/Designer) | Verifies response times and usability on desktop, tablet and mobile. |
| Quality assurance | H9 · Quality and technical closure | Full audit, coverage of the 21 business rules and documented RF/RN/CU traceability. | Computer and documents | Wk. 16 (09-12 a 15-12) | Whole team | Closes when the full test suite passes with no blocking findings. |
| Project management | Migration to production | Deploy the final version of the system to the production environment. | Computer, Docker Compose | Wk. 17 (16-12 a 22-12) | Pablo Carrera (PM/Analyst) | Delivery of the complete system with all requirements implemented. |
| Project management | Training sessions | Explain the system's use to test end users. | Computer and documents | Wk. 17 (16-12 a 22-12) | Whole team | Helps the user operate the system without issues. |
| Project documentation | User manuals | Draft the user manuals and training material. | Computer and documents | Wk. 18 (23-12 a 30-12) | Ignacio Carrera (DBA/QA/Designer) | Gives the user a guide for operating the system. |
| Project management | Project closure act | Formalize the project's closure and final delivery. | Computer and documents | Wk. 18 (23-12 a 30-12) | Pablo Carrera (PM/Analyst) | Marks the project as finished before the guiding instructor. |

8. Gantt Chart

Planned activities distributed across the 18 weeks of the academic term.

| Activity | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Charter |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team organization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Charter approval |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| General requirements definition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specific requirements capture |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Software architecture document (DAS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Extended use-case document |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mockups and navigable prototype |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ERS report and requirements sheet |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| H0 · Project scaffolding |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| H1 · Data and catalogs (DB scripts and PL/SQL queries) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| H2 · Security, accounts and SII validation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| H3 · Tenders and lazy closing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| H4 · Applications and blocking compliance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| H5 · Award and comparison matrix |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| H6 · Reputation and prestige levels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| H7 · Traceability and reports (RPT-01/RPT-02) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| H8 · Secondary application (15 maintainers) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Test environment setup |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Functional testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| User testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| H9 · Quality and technical closure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Migration to production |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Training sessions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| User manuals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project closure act |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Sources: MercadoNacional (MERNAC) Project Charter, ERS Report, WBS Matrix and Phase Costs, Gantt Chart and Extended Use-Case Document.